2020 AM ANAHEIM, CA (June 7-10) - SPEC BOOK TARGET DATES
As Of:  July 8, 2019

SPEC ROLL OUT/DISTRIBUTION:

Mid-End Jan		Distribute 2020 Staff Attending & On-Site Responsibilities (Jeanne)

Early Feb 			MS:  Distribution of Spec Instructions, Staff Spec Responsibilities & Target Dates

Early Mar			Order Binders, Tabs, Labels, etc – Order Details/Target Dates to Printer (LB/VL/RM/Printer)

SPEC DEADLINES TO MAKE BOOK:

Apr 20 (Mon)	Deadline:  FINAL Specs, Floor plans & Attachments Complete (10 a.m.)

SPEC BOOK COLLATION, PRINTING & MAIL DATE:

Apr 20-21	Spec Collation & Required Format for Printer (Luann - 2 days)

Apr 22 (am)		Book to Printer by morning (am) w/ tabs, binders, labels (LB/Rob)

Apr 27 (pm)		Proof from Printer (pm-Rob pick-up)

Apr 28 (am)		Proof Back to Printer (am-1st thing))

Apr 29 (am)		FINAL Collated Binders Back from Printer (no later than 10 am)

Apr 30 			Mail/Distribution Overnight (to receive by May 1) -- Facilities, Vendors and Staff

(To receive 30 days out from 1st day of load-in)

SPEC CHANGES – 1 Round (3 weeks’ worth – Apr 20 thru May 11):

May 11	(Mon)		Deadline:  Spec Changes (12 Noon)

May 13			Collation & Cover Sheet of Spec Changes (Luann-1 day)

May 13			Spec Changes to Printer (pm-by afternoon)

May 18			Proof Back from Printer (afternoon)

May 20			FINAL Collated Spec Changes Back from Printer – late AM

May 21 (Thurs)		Distribution/Mailing of Spec Changes – PS (receive no later than May 22)

ELECTRONIC UPLOAD TO DROP BOX (two uploads)

May 4-5		Organize electronic files and upload to Drop Box

May 5			1st Upload of Original Book Complete

May 22			2nd Upload of Spec Changes (New and Revisions) Complete

MEMORIAL DAY HOLIDAY

May 25			MEMORIAL DAY – OFFICE CLOSED

RUN DOWN OF EVENTS:

May 11			Schedule Request to CS-FS, MK-MP/SS, PC-VIP, VL-Key Areas – schedule their parts into RD

May 21-26		Input everything into Run Down

May 27			Run Down Complete to include Spec Changes - Printed (in-house copier) & Distributed

SHIPMENT:

May 26-27		All materials ready for collection in-house

May 28 (Thurs)		SHIP OUT

ANNUAL MEETING (3 weeks later than last year):

June 2			Tuesday - Staff begins leaving for Annual Meeting

JUNE 7-10		ANNUAL MEETING