## Sheet1
Date: Virtual Event - August 3-August 7, On-Demand - August 8-28
Registration Open: Tuesday, June 16th
Price: $149, members, registered mentees, academy members, agency managers, special guests (comp)
Jeanne - Overall - Budget, Vendor Management, Timeline, Event Layout
Mark | Jim/Wayne | Don | Jess | Joanne/Kristal | Joanne/Mary | Pat/Jeff | Pat/Anne/ Carolyn | Phyllis/Jeff | Phyllis/Jeff/ Michael | Jess/Erica | Luann/Lauren/ Molly/Kirsten | Pam/Suzanne | Karen Matts | Tom/Vickie | Eryn/Rosanne
Finance | IT | Marketing/Press | Programming | Registration | Sponsors & Exhibitors | Contract | Special Events | Platform Development | Speaker Visuals/Production Management/Tech Support | Translation | Landing Page, branding, transitional elements | Mentoring & CC, GC Meetings | Foundation | Survey, Membership Booth, Ann Bus Mtg | Special Guests & Agency Managers Programs
Development of Budget with Jeanne | Interface with Vendor Platform & Registration Company; real-time data transfer | Look and Feel, color palate | PDD & content organization | Registration - select and contract either MCI or Experient | Sponsorship & Exhibitors | Vendor Contract | Past Presidents - networking room. Ian's state of union presentation to PP | Vendor Platform development | Jeff - responsible for production elements, visuals and recording for the MP speakers for both meetings. Develop the visuals for the AM Focus Session | Pre-recorded translation of MP speakers into 12 languages. Live, subtitles, voice overs? | Event Landing Page layout & Branded environment | Mentor Booth - will you have one? Work with Luann/Lauren/Molly to develop | Foundation Booth - will you have one? Work with Luann/Lauren/Molly to develop | Tom will be point: Membership booth - do you want one since there are Academy and Mentees attending? If so work with Luann/Lauren & Molly | Special Guests Events
Determination if we are able to accept WeChat or Alipay by May 1 | SSO | Marketing Plan & vendor usage | Event Layout - collaborate with Meeting Services & Vendor to determine time segments for speakers and breaks for Virtual Event and On-Demand Content. Overall show flow | Develop a badge system, ribbons, reporting system, privacy statements. | Will we provide a session that is view only for our sponsoring companies? |  | Quarter Century - networking room | Confirm Time zones - Everyone begins at 8:00 am on Monday in their time zone (tier open rollout) or we open at 8 am Central and then everyone joins when they can | Michael - manage the recording and develop the visuals of the Global Conference Focus Session and ConneXion Zone speakers. Manager the recording of AM FS and CZ Speakers and assist Jeff with visuals | Pre-recorded translation of FS & CZ Speakers for the languages that do not have Language Specific Sessions. Live, subtitles, voice overs? | Transitional elements between speakers: videos, exercise (chair yoga), meditation, etc. | Committee Chairs and/or Global Council. Will this occur? If so work with Phyllis and Jeff to incorporate into platform. Jess and Jeanne to incorporate into schedule | Service Project or Fund Raising. Ticker tape on bottom listing donors. Runnign total box... | Vickie will be point: Survey Monkey integration, do own, evaluate vendor offering? | Agency Managers
Is there a reason to insure this event? | Ability to Flag specific groups (COT/TOT, Members for An Bus Mtg) | Store offering - Once decided work with Lauren B | Speaker Training and Rehearsals | Provide website copy with MarCom as information becomes available | Advertisments |  | Top of the Table - networking room; Past Chairs state of the union by Clay | Concurrent users | Michael - Sponsorship session visuals - if offer special viewing. Any visuals for CZ Sponsorship session | Live Q & A of Focus Session Speakers - who will handle? Language specific session handled by speaker, translated into other areas - do we use captains or PGA members to moderate and facility in native language? | Gamification: Leadership Board, Scavenger hunt, video games, etc. |  |  | Tom/Barbara will be point on this: Annual Business Meeting - Do we need to incorporate into the platform or use the attendee list and send to members?
| Can the vendor handle questions from the live Q & A sessions in country characters? | Press - will they be involved? | MP Emcee? FS Moderators - use PGA or PDC? | Ensure GDRP Compliant | New Opportunities |  | PDC/PGA Dinner - replace with a virtual award ceremony | Recording of Sessions | Jeff - Tech Support/Help Desk. Ensure we have the correct coverage/languages | Other interpretation requirements? | Networking room for attendees
| Security Platform - Hackers |  | Chat Rooms/Questions during live Q & A. Are they with speaker/moderator or peer to peer? | Work with Jim and Wayne to ensure integration |  |  |  | Work with Jim and Wayne to ensure integration | check audio/lighting for speaker recording |  | Foundation, Store, Sponsors, Mentor Booth - included in landing page
| Does the platform work globally |  | Will you reqiure an ARS system? | Are we including Press | [6 empty] | Avatars using PGA
|  |  |  | FAQ sheet - work with MarCom to develop. Share with Member Services and Global Markets to manage calls | [6 empty] | Reserved Seating - is it a possibility?